## Issue report
Title: |  | Community Module for extension version
Project |  | Project Name: eMIS |  |  | Legend
Environement |  | Development server(Demo) |  |  |  | New |  |  | 693043
Tester: |  | Tester: Mejbah jaman utsah |  |  |  | Done
Development |  | eMIS development team (icddrb) | PoviderID: 93068 |  |  | In progress
OS |  | Android (5.1) |  |  |  | Reopened
Tab Model |  | Sumsong GALAXY Jmax |  |  |  | Pipeline
Further discussion needed
Issue ID | Issue No | Module | Issue Short Summary | Steps to Reproduce | Actual Result | Expected Result | Issue Image | Priority | Issue Category | Status | Developer Feedback | Tester Feedback | Comments
ID001 |  | Login module | Logged in does not sucessfully | 1. Goto the application login page 2. Put user name and Password 3. Click login button 4. Observe the page | not login | should be Logged |  | Critical |  | Falil |  | DOne
ID002 |  | Homepage >> Advertizing part | After cliking Advertizing image then its redirect to worng page/part | 1. Goto the home page after using web URL 2. Goto the Adverting part 3. Click the Adverting image 4. Observe the page | Now redirect to scrolling image part | Advertizing page should be display after the Advertizing image |  | Low | Functional | New
ID0003 |  | Contract Us | Blank testing in Contrat us page | 1. Goto the QA harbor page 2. Click Cantarct Us link 3. Click Send Button with all fileds are Blank 4. Observe the page | Now displaying " One or more fields have an error. Please check and try again." | 1. Display the understable validation message after each filed/ especially mandatory field |  | High
ID0004 |  | Contract Us | All special charters are not supported in to the Name filed | 1. Goto the QA Harbor Home page 2. Click SQA Expert Agumentation under Services 3. Goto the Augmentation part under "Choose your desired package" table 4. Click Hire Noe Button 5. Filled up the Contract us form , Especially use All Special charaters in Name filed 6. Click Submit button then Oveservr the page | All Special charaters in Name filed suppoted or succesfully added | Only Charters ( A-Z/a-z) and Spec () would be supported or inputted |  | Hi

## TC
Test ID | Pre-condtition | Decsrption | Steps | Expected result | Actucal result | Pass | Fail | Priority | Commet
TC001 | Need login credents | Logged in succcessflly | 1. Goto the web URL 2. Input username 3. Input password 4. Click submit button | Logged succhly with profile | Now show user loogged profile page | Pass |  | High