## LinenTech Test Summary
LinenTech Test Summary
Module Name | Work Status | Bug Count | [5 empty] | Total (Module Wise)
|  | Blocker | Critical | High | Medium | Low | Suggestion
Login | Not Started
Admin | Not Started
Driver | Not Started
Staff | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blocker | A bug that completely stops a process, requiring immediate attention.
Critical | Severe issues that significantly affect program's output functionality, demanding urgent resolution.
High | Important bugs with a notable impact on performance, needing prompt attention.
Medium | Moderate issues that affect the program but aren't urgent, can be addressed soon.
Low | Minor issues with minimal impact, can be addressed at a later time.

## LinenTech Bug report
Created By | QA Harbor Limited |  | Title | Issue report for LinenTech | Website URL | https://suzu-service.com/linentech/ | Environment | Windows 10,Google Chrome 131.0.6778.86 MacOS Linux Browser: Chrome,Mozilla firefox,Microsoft Edge
Bug ID | Module | Issue Type | Issue Summary | Steps to reproduce | Expected result | Actual result | Attachments | Priority | Bug Status | Dev Comment | Tester Comment | Date
Issue_0001 |  |  | Deactivated items are displayed in the product leasing list. | 1.Navigate to the url: https://suzu-service.com/linentech/ 2.Login as admin 3.Click on settings 4.Go to Inventory room and edit 5.See the product name | Deactivated items should not be visible or selectable in the product leasing list | Deactivated items are displayed in the product leasing list. | https://drive.google.com/file/d/11EcQcq31ybAUalgyd4bJAJYARJmBzFIs/view?usp=drive_link | Low | Closed | If the product is assigned in any room and InStock>0 then In active is not possible, other wise It will in-active and from all inventory rooms ut will remove. As well the Product type. If for selected product type's all the rooms InStock is 0 then all the product of this type also will inactive also from all rooms all the roducts of this type will remove.
Issue_0002 |  |  | The hospital name accepts long text input, but after some time, it automatically shortens the name, even when changed to Japanese characters. | 1.Navigate to the url: https://suzu-service.com/linentech/ 2.Login as admin 3.Click on settings 4.Go to hospitals and input long text to hospital name field 5.See the product name | The hospital name should remain unchanged and have text limit, without being shortened automatically. | The hospital name accepts long text input, but after some time, it automatically shortens the name, even when changed to Japanese characters. | https://drive.google.com/file/d/1i_t2e40-q3wwKYY2k0G9Jfp36tBq-90z/view?usp=drive_link | Low | Not a bug
Issue_0003 |  |  | When attempting to collect, the system requires 3 pieces but displays Collected: 2 Pcs and Collection Difference: -2 Pcs even though the stock count is 0 | 1.Navigate to the url: https://suzu-service.com/linentech/ 2.Login as Staff 3.Click Add Collections 4.Select Hospital and give unit number 5.Observe the collected number | Since the stock count is 0, the system should not allow collection and should display Collection Difference: -3 Pcs | When attempting to collect, the system requires 3 pieces but displays Collected: 2 Pcs and Collection Difference: -2 Pcs even though the stock count is 0 | https://drive.google.com/file/d/1iQY_3o8hXypnN8k_7qi0bH0YFEupO0uD/view?usp=drive_link | Medium | Not a bug
Issue_0004 |  |  | When trying to create a lease and change the Inventory Room under Leased Products, the room number does not update automatically | 1.Navigate to the url: https://suzu-service.com/linentech/ 2.Login as admin 3.Create a new lease and select hospital which has 2 inventory rooms 4.Now select different room and observe the lease products inventory room number | The room number should update automatically when a different Inventory Room is selected under Leased Products | When trying to create a lease and change the Inventory Room under Leased Products, the room number does not update automatically | https://drive.google.com/file/d/1dykKYqUYFm5p7dMbLBVKRwwUcAhm1Vm0/view?usp=drive_link | Medium | Not a bug
Issue_0005 |  |  | A duplicate product leasing entry is created when leasing from a new account for the first time. | 1.Navigate to the url: https://suzu-service.com/linentech/ 2.Login as driver 3.Lease product and observe the result | Leasing a product from a new account for the first time should create only a single entry, with no duplicates. | A duplicate product leasing entry is created when leasing from a new account for the first time. | https://drive.google.com/file/d/1DlaIbNxEOx3fmcenOhr14tKfnnUHceEy/view?usp=drive_link | High | Closed
Issue_0006 |  |  | Password validation blocks valid user creation. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to User → Add New. 3. Enter details: • Name: “Test” • Email: “ontorhazari571@gmail.com” • Password: “Paw0rd!” • Confirm Password: “Paw0rd!” • Other fields filled normally. 4. Click Add New. | User should be created successfully with the given valid password. | Validation error shown: “Password should be minimum 6 characters with number, letter and symbol.” | Issue_0004_Validation_Error.png | High | Not a bug |  | Issue occurred during dev updates; it's fixed now, mark as 'Not a Bug'.
Issue_0007 | Settings (Hospitals - Add New) |  | Cross-Site Scripting (XSS) vulnerability in Hospital Name field. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings → Hospitals. 3. Click Add New. 4. In Hospital Name, enter: <script>alert('2')</script>. 5. Enter Room Number: “234”, set Status: “Active (A)”. 6. Click Add New. 7. Refresh or view the Hospitals list. | Hospital name should be sanitized (e.g., &lt;script&gt;alert('2')&lt;/script&gt;) and displayed safely with no script execution. | Hospital added successfully (ErrorCode: "00", "Success"), but script executes on page load — alert(‘2’) popup appears. | Issue_0005_XSS_HospitalField.png | High | Not a bug |  | XSS issue isn’t in current scope, mark as 'Not a Bug'
Issue_0008 | Settings (Inventory Room - Add New) |  | Cross-Site Scripting (XSS) vulnerability in Room Name field. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings → Inventory Room. 3. Click Add New. 4. Select Hospital Name 5. In Room Name, enter: <script>alert('1')</script>. 6. Add a product: Product ID=6, Name: “p2”, Capacity: 10. 7. Set Status: “Active (A)”. 8. Click Save. 9. Refresh or view the Inventory Room list. | Inventory room name should be sanitized (e.g., &lt;script&gt;alert('1')&lt;/script&gt;) and displayed safely without script execution. | Inventory room added successfully (ErrorCode: "00", "Success"), but script executes on page load — alert(‘1’) popup appears. | Issue_0006_XSS_RoomField | High | Not a bug |  | XSS issue isn’t in current scope, mark as 'Not a Bug'
Issue_0009 | Settings (Hospitals - Add New) |  | Popup closes and data is lost when adding a hospital with a duplicate name. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings → Hospitals. 3. Click Add New. 4. Enter a duplicate Hospital Name (e.g., “Test Duplicate Hospital Name”). 5. Fill Inventory Room (e.g., “H5”) and set Status: “Active”. 6. Click Add New. | Validation error (“Duplicate hospital name”) displayed inline; popup stays open so users can fix it without losing data. | Brief error message shown, then popup closes automatically. User must reopen Add New and re-enter all data. | Issue_0007_Duplicate_Hospital.mp4 | Low | Not a bug
Issue_0010 | Settings (Hospitals List) |  | “No Data” label in table header is misaligned. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings → Hospitals. 3. Ensure no hospitals are added. 4. Observe the table header row display. | “No Data” label should be left-aligned and vertically centered in the header row for consistent UI. | “No Data” label appears misaligned (centered horizontally, potentially off vertically), affecting header aesthetics. | Issue_0009_NoData_Misaligned | Low | Closed
Issue_0011 | Settings (Hospitals List) |  | Table columns misaligned after adding hospital data. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings → Hospitals. 3. Add a new hospital (e.g., Name: “Test H3”, Inventory Room: “103”, Status: “Active”). 4. View the updated table list. | All table columns properly left-aligned with consistent padding and vertical centering in both header and data rows. | Data rows show misalignment (e.g., “102” and “Active” not flush left under headers, inconsistent spacing), persisting from empty state. | Issue_0010_Columns_Misaligned.png | Low | Not a bug
Issue_0012 | Settings (Inventory Room List) |  | Edit icons (pencil) in Inventory Room table rows are misaligned, appearing to overlap cell borders or content. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings → Inventory Room. 3. Ensure data exists (add rooms if needed, e.g., Sunrise Medical Center - R101). 4. Observe the table rows and edit icons. | Edit icons properly right-aligned within the action cell of each row, with adequate padding and no overlap. | Edit icons misaligned (e.g., protruding into cell borders or uneven spacing), disrupting row aesthetics. | Issue_0012_EditIcon_Misaligned | Low | Not a bug
Issue_0013 | Reports (Inventory Report Export) | Functional | Export ignores hospital filter and includes data for all hospitals. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Reports → Inventory Report. 3. Select a specific hospital (e.g., “Sunrise Medical Center”) from the dropdown. 4. Click Export. 5. Open the exported file (e.g., Excel sheet). | Exported file contains only data for the selected hospital (e.g., only “Sunrise Medical Center” items). | Exported file includes data for all hospitals (e.g., Sunrise Medical Center, D1 Hospital, Greenfield Hospital), same as “All Hospitals” export. | Issue_0013_Export_Filter | High | Closed
Issue_0014 | Reports (Ledger Report Export) |  | Export only includes the visible page, missing data from other pages. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Reports → Ledger Report. 3. Set pagination to 10 rows per page. 4. Confirm multi-page data exists (e.g., page 2 ID “L25020007”). 5. Return to page 1 and click Export. 6. Open the exported Excel file. | Exported file contains the complete dataset from all pages (e.g., entries from page 1 and page 2 like ID “L25020007”). | Exported file only includes data from the visible page (first 10 rows; ID “L25020007” from page 2 is missing). | Issue_0014_Ledger_Report | High | Closed |  | This issue exists in other features, so I am not creating a new issue
Issue_0015 | Reports (Inventory Report) | UI | Inventory Report Page Shows No Message for Hospitals with No Data | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Reports → Inventory Report. 3. Select a hospital with no inventory data (e.g., “Greenfield Hospital”). 4. Observe the report content area. | Report area displays a clear “No Data” message or placeholder (e.g., centered text like “No inventory data available for this hospital”) for better UX. | Report area shows a blank white box with no content or indication of empty data, confusing users. | Issue_0015_Blank_Report | Low | ReOpen |  | This issue is not fixed. When selecting any hospital in the filter, if the hospital has no data, the inventory report page does not display any message such as 'No data' or anything else
Issue_0016 | Settings-Inventory Room |  | When updating the product capacity of any inventory room, an error message is displayed, but the updated number is still saved. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Settings and then inventory room 3.Click on any product and try to update the capacity and observ ethe result | The system should either save the updated capacity without showing an error or display an error and prevent the update from being saved. | When updating the product capacity of any inventory room, an error message is displayed, but the updated number is still saved. | https://drive.google.com/file/d/1G1BUY_yjKvLjjhxs_eyO0I2Czo9w8yFG/view?usp=drive_link | High | Closed
Issue_0017 | Create new lease |  | When trying to initiate a lease with Lease Qty: 10 while In-Stock: 30 and Capacity: 10, the system displays an error and automatically sets Lease Qty to -20, showing the message Exceed Capacity. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2.Login as Driver 3.Lease a product which has In-Stock: 30 and Capacity: 10 4.Input lease Qty 10 and observe the result | The system should not display an incorrect negative lease quantity. It should either prevent leasing beyond capacity with a proper validation message or allow the lease only if it meets the capacity limit. | When trying to initiate a lease with Lease Qty: 10 while In-Stock: 30 and Capacity: 10, the system displays an error and automatically sets Lease Qty to -20, showing the message Exceed Capacity. | https://drive.google.com/file/d/14GLNMYpJg1Lx1OCFb9qY1r2-BONmOEPL/view?usp=drive_link | High | Closed
Issue_0018 | Reports (Loss Report Export) |  | Loss Report export displays "No Define" in the exported file title instead of "Loss Report". | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Reports → Loss Report. 3. Ensure data exists (e.g., Hilltop Community Hospital entries). 4. Click Export. 5. Open the downloaded XLSX file. | File named "Loss Report.xlsx" with "Loss Report" as title. | File named "No Define20251022183.xlsx" with "No Define" in cell A1. | Issue_0018_LossReport_Title. | Low | Closed |  | please check Issue_0018. This problem occurs not only in the Loss Report but in all export features — the exported file title shows 'No Define' instead of the actual report name.
Issue_0019 | Audit (Audit Page) |  | Header shows “No Define” instead of “Audit ”; also in Status dropdown. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Audit page. 3. Observe the page title | Title is “Audit ” | Title is "No Define". | Issue_0019_Audit_NoDefine.png | Low | Closed
Issue_0020 | New Collection |  | No space between search box, pagination box ("Show 10 Every Page") | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Dashboard → Collections → +Add Collection. 3. Observe Products table: search box, pagination (“Show 10 Every Page”). | Proper spacing between search box, pagination box, | pagination box overflows/overlaps search box | Issue_0020_UI_Spacing.png | Low | Closed
Issue_0021 | In Android | UI | The password field on the login page displays two eye (visibility toggle) icons instead of one, causing a UI inconsistency. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Observe the UI | The password field should display only one eye icon to toggle password visibility, ensuring a clean and consistent user interface. | The password field on the login page displays two eye (visibility toggle) icons | https://drive.google.com/file/d/1aqKKa8cxqC8DB6jMBNo1UsCRHkGsQAc2/view?usp=drive_link | Low | Closed | one is browser default
Issue_0022 | In Android |  | In the driver leasing section, the "Leased Product" area is too narrow, making it difficult to scroll and view the listed products properly. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver 3.Lease an item and observe the result | The "Leased Product" section should be wider and provide enough space for smooth scrolling and clear visibility of all products. | In the driver leasing section, the "Leased Product" area is too narrow, making it difficult to scroll and view the listed products properly. | https://drive.google.com/file/d/1YQJi9wakIUMwIeUdswimBUh8r6Nip2uQ/view?usp=drive_link | Low | Closed
Issue_0023 | In Android |  | There is a UI issue in the search section of the dashboard — the layout is out of scope | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver 3.Observe the dashboard UI | The search section in the dashboard should be properly aligned and visually consistent with the overall UI design. | There is a UI issue in the search section of the dashboard — the layout is out of scope | https://drive.google.com/file/d/1MJHTExiXo27GAEjyAxA7-uQY0ocF64fM/view?usp=drive_link | Low | Closed
Issue_0024 | In Android |  | The date search UI is not displayed in the dashboard properly | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver 3.Observe the dashboard UI | The date search UI should be visible and functional | The date search UI is not displayed in the dashboard properly | https://drive.google.com/file/d/1jXU2NqWLX6kbZHmzsfj8BqsOpRJE-BCC/view?usp=drive_link | Low | Closed
Issue_0025 | In Android |  | After searching by date, there’s no option to clear the entered date. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver 3.Observe the dashboard UI | A clear or reset option should be available to remove the entered date easily. | After searching by date, there’s no option to clear the entered date. | https://drive.google.com/file/d/1j-basSDKwi_Lm-yXB9epphZphwXCBhwM/view?usp=drive_link | Low | Closed
Issue_0026 | Audit (Audit Page) |  | After auditing a product, it shows a Pending status, but when clicking on the ticket, it incorrectly displays Delivered. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as Admin 3.Go to audit 4.Add product and save the audit 5.Click on the pending ticket and observe the result | The ticket status should consistently reflect Pending until it is actually delivered. | After auditing a product, it shows a Pending status, but when clicking on the ticket, it incorrectly displays Delivered. | https://drive.google.com/file/d/1BRr1SFxADt8hy0VIEn5AWpZ-jkxXZrEk/view?usp=drive_link | Medium | Closed
Issue_0027 | Audit (Audit Page) |  | There is no option to confirm Pending tickets created during the audit. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as Admin 3.Go to audit 4.Add product and save the audit 5.Click on the pending ticket and observe the result | There should be a functionality to confirm or update Pending tickets after an audit. | There is no option to confirm Pending tickets created during the audit. | https://drive.google.com/file/d/1BRr1SFxADt8hy0VIEn5AWpZ-jkxXZrEk/view?usp=drive_link | High | Closed
Issue_0028 | Audit (Audit Page) |  | After completing an audit and marking it as delivered, a message box appears but it is blank. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as Admin 3.Go to audit 4.Add product and save the audit 5.Confirm the audit | A success message should be displayed inside the message box after the audit is marked as delivered. | After completing an audit and marking it as delivered, a message box appears but it is blank. | https://drive.google.com/file/d/1G0m3e0ueXHvCku4PMz0TSLsnf9c6hD3O/view?usp=drive_link | Low | Closed
Issue_0029 | In Android |  | After adding a product for pre-collection, display a success message like “Product added” . This will help users confirm that the product was successfully added. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver 3.Click on pre collection and add any product to the list |  |  | https://drive.google.com/file/d/1QiUXsvdj2f8SFsc24g25dj-OKlLciCWC/view?usp=drive_link | Suggestion | Not a bug | No need
Issue_0030 | Pre collection page |  | Show both pre-collection and actual collected quantities so the driver can easily track completion. | Pre-collection information and collection information are different. For example, if the pre-collection quantity was 10 pcs but only 7 pcs were collected, the driver won’t know that the collection was completed with 7 pcs. | Show both pre-collection and actual collected quantities so the driver can easily track completion. |  | https://drive.google.com/file/d/1Eb_p8bog9DOx54DQegToruo5OkIxQxcU/view?usp=drive_link | Suggestion | Not a bug | pre collection quantity is bag quantity not item quantity, please note that, when collection is occuring from pre-collection then the collected item's quantity will calculate accroding the given weight and product weight
Issue_0031 | Profile |  | The user is unable to update their profile. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver,staff,admin 3.Go to profile section 4.Try to update user name | The user should be able to successfully update their profile | The user is unable to update their profile. | https://drive.google.com/file/d/1Zrf50dFYOjwmCEn70f8d-vbJblnOmhxi/view?usp=drive_link | High | Closed
Issue_0032 | profile |  | The error messages displayed are not proper or clear. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver,staff,admin 3.Go to profile section 4.keep all field blank and observe the error message | Proper and clear error messages should be displayed when an update fails. | The error messages displayed are not proper or clear. | https://drive.google.com/file/d/158TV20tC1xE4Yle9T67njD08hGJkelXn/view?usp=drive_link | Low | Not a bug | need to set, back end language fixng
Issue_0033 | Dashboard - iPad Pro 13-inch (2024, iOS 17.5) - safari |  | Date input field fails to open calendar popup on click. | 1. Use iPad Pro 13-inch (2024) with iOS 17.5. 2. Log in to https://suzu-service.com/linentech/ in browser. 3. Navigate to Dashboard. 4. Click on the date search field (“yyy/mm/dd”). | Calendar popup opens for date selection. | No popup appears; field does not respond. | Issue_0033_iPad_DatePicker_img.jpg Issue_0033_iPad_DatePicker_vedio.mp4 | Medium | Closed
Issue_0034 | Login Page Create user form |  | The email field has no validation on both the Create User form and the Login page. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to user section and create user 4.Input invalid email in the email field 5.Login using the created user credentials | The email field should have proper validation to ensure only valid email formats can be submitted on both the Create User form and the Login page | The email field has no validation on both the Create User form and the Login page. | https://drive.google.com/file/d/1zY86pjrFW-cNAdn5FNtNNzuvysH_566J/view?usp=drive_link | Suggestion | Not a bug | no need
Issue_0035 | Dashboard (Search Date Picker)- iPad Pro 13-inch (2024, iOS 17.5) - safari |  | Date picker fails to open sequentially on iPad when clicking search. | 1. Use iPad Pro 13-inch (2024) with iOS 17.5. 2. Log in to https://suzu-service.com/linentech/ in browser. 3. Navigate to Dashboard. 4. Click on the date search field (“yyy/mm/dd”) then search. | Date picker opens sequentially for date selection on click. | Date picker fails to open sequentially; no response or incorrect behavior. | Issue_0035_iPad_DatePickerSearch_img.jpg Issue_0035_iPad_DatePickerSearch_vedio | Medium | Closed
Issue_0036 | Password Page |  | In the password section, the old password field shows the entered text instead of hiding it | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to profile and password section 4.Input password to the old password section and observe the result | The old password field should hide the entered text with dots, just like the other password fields | In the password section, the old password field shows the entered text instead of hiding it | https://drive.google.com/file/d/1Hreb3oqVa2HHJkRrbcaF13fZJMvjW9j9/view?usp=drive_link | Low | Closed
Issue_0037 | Leasings (Create New Lease Form))- iPad Pro 13-inch (2024, iOS 17.5) - safari |  | UI overlap: ProductName and LeaseQty columns overlap with no space in Leased Products table. | 1. Log in as Driver at https://suzu-service.com/linentech/. 2. Navigate to Dashboard → Leasings. 3. Click “Add Lease” to open Create New Lease page. 4. Observe Leased Products table. | Columns (ProductName, LeaseQty) properly spaced without overlap. | ProductName and LeaseQty overlap with no space between them. | Issue_0037_iPad_LeaseUIOverlap_img.jpg | Low | Closed | iPad Pro 13-inch (2024, iOS 17.5)
Issue_0038 | Leasings (Update Lease Form)- iPad Pro 13-inch (2024, iOS 17.5) - safari |  | Clicking “Initial Lease” without values in ProductName and LeaseQty breaks those input fields. | 1. Log in as Driver at https://suzu-service.com/linentech/. 2. Navigate to Dashboard → Leasings. 3. Click “Add Lease” to open Create New Lease page. 4. Then select the Hospital Name then click Add Button 5. Click initial Lease Button | Form validates (e.g., shows error) or processes without breaking fields; UI remains intact. | ProductName and LeaseQty fields break (e.g., UI distortion, misalignment, or non-responsive). | Issue_0038_iPad_LeaseFieldBug.jpg | Low | Closed | iPad Pro 13-inch (2024, iOS 17.5)
Issue_0039 | User page |  | On the User page, there is no clear button to reset the search filters | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to profile and password section 4.Input password to the old password section and observe the result | A clear button should be available on the User page to reset or clear the applied search filters. | On the User page, there is no clear button to reset the search filters | https://drive.google.com/file/d/1bIgME_anlivd7EJprUzcCK5Ao54Su7eB/view?usp=drive_link | Low | Closed
Issue_0040 | Settings-Inventory Room |  | When searching with filters, the search bar retains the entered data, but the search results automatically reset to the default view. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to settings and then inventory room 4.Use filter for search hospital and update any information of the search result data 5.Update and observe the list and the filter section | The search results should display based on the applied filters and should not reset to the default view while the filter data remains. | When searching with filters, the search bar retains the entered data, but the search results automatically reset to the default view. | https://drive.google.com/file/d/1NuUQfHRRNlpZso1vDyVEOL0otfmAsOXb/view?usp=drive_link | Medium | Closed
Issue_0041 | Pre collection page |  | The pre-collection form shows the wrong driver name even after logging in as a driver. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as driver 3.Go to the pre collection form 4.Add item for pre collection and observe the name of teh driver | The pre-collection form should display the correct driver name based on the logged-in driver’s account. | The pre-collection form shows the wrong driver name even after logging in as a driver. | Issue_0040_Wrong_DriverName.png | Medium | Closed
Issue_0042 | Loss report |  | The Loss Report displays incorrect data that doesn’t match any actual performed actions. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to report and select loss report 4.Observe the report section data | The Loss Report should display only accurate data based on actual performed activities. | The Loss Report displays incorrect data that doesn’t match any actual performed actions. | https://drive.google.com/file/d/1vyTBMT3ydSYM7VpSVwgrFhK4hPG25XXQ/view?usp=drive_link | High | Closed |  | This issue again displayed https://drive.google.com/file/d/1CK2ro9KlhLR5sQyJ47hu-iKOxP8igszv/view?usp=drive_link Loss Report_11/11/25 https://drive.google.com/file/d/1-GboigEwwjzHi07K9ytFlSojwgwodw0S/view?usp=drive_link
Issue_0043 | Audit (Audit Page) | Functional | Bug: In the audit functionality, an error appears when trying to input an audit stock value of 0. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to Audit and input 0 in the audit stock | The system should allow entering 0 as an audit stock value if applicable, or show a proper validation message explaining why 0 is not allowed. | Bug: In the audit functionality, an error appears when trying to input an audit stock value of 0. | https://drive.google.com/file/d/1rTqSKhs5EZcFSxKWeY9UFjKRoQubWgFG/view?usp=drive_link | High | Closed | In here if instock=AuditStock,no data save, | Now user can't input audit stock less than stock.Then why need audit feature? https://drive.google.com/file/d/1P5o17iD43nD5oWTBp9lB1MSPGVXgQF7k/view?usp=drive_link
Issue_0044 | Pre collection page | Functional | In the leasing section, pending orders are added to the top, but in the pre-collection section, pending orders are added to the bottom. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to pre collection section and add new pre collection order | Pending orders in the pre-collection section should also be added to the top to maintain a consistent order. | In the leasing section, pending orders are added to the top, but in the pre-collection section, pending orders are added to the bottom. | https://drive.google.com/file/d/1lAWqLNGj_P5rV2K5Lp1yww8gU9eaHLkZ/view?usp=drive_link | Low | Closed |  | In pre collection newly created pre collection added to the bottom of the list.
Issue_0045 | UI |  | The "Clear" button is displayed only as text and is not highlighted or boxed like other buttons. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Search any item from any page and observe the result | The "Clear" button should be highlighted and styled with a box, consistent with other buttons. | The "Clear" button is displayed only as text and is not highlighted or boxed like other buttons. | https://drive.google.com/file/d/1AdbuW-J3LGrcoHiOATRqFtJ75n4R35CB/view?usp=drive_link | Suggestion | Not a bug | all are clear style is same
Issue_0046 | Audit (Audit Page) |  | When preparing an audit, the system displays the wrong date and time. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to Audit section and prepare one audit | The correct current date and time should be displayed when preparing an audit. | When preparing an audit, the system displays the wrong date and time. | https://drive.google.com/file/d/1eHeKtidociu5aPwV9wB61CqDkzSAw-V5/view?usp=drive_link | High | Closed | It comes When Selected hospital and selected Room has existing data | Got it fixed now
Issue_0047 | Settings-Product |  | An unclear error message appears when trying to deactivate a product. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Go to Product section 4.Deactivated any stored product and observe the result | A clear and meaningful error message should be displayed when deactivating a product | An unclear error message appears when trying to deactivate a product. | https://drive.google.com/file/d/1pdopYI9udXLvXrW2pMHq5DbQPFn7U2Ma/view?usp=drive_link | Medium | Closed
Issue_0048 | iPad Air |  | The search section overlaps with another section when perform search action | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as admin 3.Search using date filter and observe the result | The search section should stay in its position without overlapping other sections. | The search section overlaps with another section when perform search action | https://drive.google.com/file/d/1dPCQVX9oe6WIbfYY-XNTpUoawMdTLFwM/view?usp=drive_link | Low | Closed
Issue_0049 | iPad Air |  | The Cancel, Save, and Confirm buttons appear congested and too close to each other. | 1. Navigate to the link https://suzu-service.com/linentech/. 2.Login as Staff 3.Go to collection and Add new 4.Input one product unit and observe the result | There should be proper spacing between the Cancel, Save, and Confirm buttons for better visibility and usability. | The Cancel, Save, and Confirm buttons appear congested and too close to each other. | https://drive.google.com/file/d/162LQx_R0aep0lB4Plwz6NRl0SazeZr70/view?usp=drive_link | Low | Closed
Issue_0050 | Dashboard - iPad (7th generation) with iPadOS 18.5 - Safari |  | Dashboard UI is broken when logged in as Driver on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5. 2. Log in as Driver at https://suzu-service.com/linentech/. 3. Navigate to Dashboard. 4. Observe the UI layout. | Dashboard title, date selectors, and search button displayed horizontally in a row; “Leasings”, “Pre-Collections”, and “Add Lease” button properly placed side-by-side or in intended layout without misalignment. | Dashboard title, date selectors, and search button displayed vertically stacked; “Leasings”, “Pre-Collections”, and “Add Lease” button misplaced or not in proper positions. | Issue_0043_iPad_DashboardUI.png | Medium | Closed |  | iPad (7th generation, iPadOS 18.5, Model MW742LL/A), 3.2s
Issue_0051 | Leasings (Create New Lease Form) - iPad (7th generation) with iPadOS 18.5 - Safari |  | Product Name dropdown has elements but is not understandable; requires scrolling to find items. | 1. Log in as Driver at https://suzu-service.com/linentech/. 2. Navigate to Dashboard → Leasings. 3. Click “Add Lease” to open Create New Lease page. 4. Select Hospital Name (e.g., Hilltop Comm). 5. Click “Add” button. 6. Click Product Name field to open dropdown. | Dropdown displays clear, understandable product items without needing excessive scrolling. | Dropdown shows elements but is unclear; scrolling required to locate items. | Issue_0044_iPad_LeaseDropdown.png | Low | Closed |  | This issue hasn’t been fixed. Issue_0051_Retest_iPad_LeaseDropdown.png
Issue_0052 | Collections (Pre-Collection Form) - iPad (7th generation) with iPadOS 18.5 - Safari |  | Added row in Pre-Collection appears broken: misaligned columns (Hospital, Type Name, Bag/Qty), titles not bold. | 1. Log in as Driver at https://suzu-service.com/linentech/. 2. Navigate to Dashboard → Collections → Add Collection. 3. In Pre-Collection, click “Add New”. 4. Fill: Hospital = “Hilltop Community Hospital”, Type Name = “Mask”, Bag (Qty) = 10. 5. Click “Add”. 6. Observe the new row. | New row displays aligned columns with bold titles for Hospital, Type Name, Bag/Qty. | Row broken/misaligned; titles not bold, difficult to understand. | Issue_0045_PreCollection_RowUI.png | Low | Closed |  | iPad (7th generation, iPadOS 18.5, Model MW742LL/A)
Issue_0053 | Login Page |  | The “Forgot Password” option is missing from the login page. | 1.Go to login page: https://suzu-service.com/linentech/. 2.Observe the page | A “Forgot Password” link should be available on the login page to allow users to reset their password easily | The “Forgot Password” option is missing from the login page. |  | Suggestion | Not a bug | no need
Issue_0054 | Loss report |  | When filtering the dashboard by date, hospital, and products, it displays incorrect data that doesn’t match the Loss report data. | 1.Go to login page: https://suzu-service.com/linentech 2.Go to the Loss report section 3.Using filter for search data. 4.Apply filters for date, hospital, and products. 5.Compare the displayed dashboard data with the loss report data. | The dashboard should display accurate data matching the filtered report results. | When filtering the dashboard by date, hospital, and products, it displays incorrect data that doesn’t match the Loss report data. | https://drive.google.com/file/d/1610Gnr4Nm538DJmguzbxpBcPKwrsOozq/view?usp=drive_link | High | Closed | Need Discussion | Please see the video: https://drive.google.com/file/d/1MUanGURa5ssH3XPO3Pwv6bakIgCzaxMZ/view?usp=drive_link Updated Attachmanet 11/11/25 https://drive.google.com/file/d/1zzYw4EOLJsl1DPEge1amijP5Qfy7ysug/view?usp=sharing 11/13/25 Attachment https://drive.google.com/file/d/1rqujsv4RCRwTFuDhAgS95WmFaWP9Dx2C/view?usp=sharing
Issue_0055 | Collections (New Collection Form) - iPad (7th generation) with iPadOS 18.5 - Safari |  | Products table requires left-to-right and right-to-left scrolling; layout not user-friendly or understandable. | 1. Log in as Staff at https://suzu-service.com/linentech/ 2. Navigate to Dashboard → Collections → Add Collection. 3. Observe the New Collection page and “Products from Collection Bin” table. | Table fits on screen without horizontal scrolling; layout is simple and clear. | Table requires horizontal scrolling (left-to-right and right-to-left); users find it difficult to view and understand data. | Issue_0055_iPad_CollectionTable_1.PNG Issue_0055_iPad_CollectionTable_2.PNG | Low | Closed |  | Need full-page UI improvement, for tab view.
Issue_0056 | DashBoard - iPad (7th generation) with iPadOS 18.5 - Safari |  | Inconsistent date formats are displayed for the "Start Date" and "End Date" fields. | 1. Log in to https://suzu-service.com/linentech/ 2. On the DashBoard page, locate the date filter section. 3. Select a date for the first field (Start Date). 4. Use the Tab key to move to the second field (End Date) and select a date. 5. Observe the text formats displayed in the two date fields. | Both the "Start Date" and "End Date" fields should display the selected dates in the same, consistent format (e.g., YYYY/MM/DD or MMM DD, YYYY). | The "Start Date" field displays the date in one format (e.g., 2025/11/12), while the "End Date" field displays it in a different format (e.g., Nov 17, 2025). | Issue_0056_iPad_DateFormat.png | Low | Closed |  | iPad Pro 13-inch (2024), iOS 17.5
Issue_0057 | iPhone 14 pro max |  | The Initial Lease button appears too low on the page. Users need to scroll down to find it. | 1. Log in as driver at https://suzu-service.com/linentech/ 2. Click on add Lease and observe the result | The Initial Lease button should be visible at the top of the page without scrolling | The Initial Lease button appears too low on the page. Users need to scroll down to find it. | https://drive.google.com/file/d/17RPdy748X3r3tp2t3zGOQnsdNLT8W3ky/view?usp=drive_link | Low | Closed
Issue_0058 | iPhone 14 pro max |  | Remove the extra blank space in the Collection page that looks like a button to improve layout clarity. | 1. Log in as staff at https://suzu-service.com/linentech/ 2. Click on Add collection and observe the result |  |  | https://drive.google.com/file/d/1SynAXkLklBmfxJRUJSUsvaGzrI3iBCJa/view?usp=drive_link | Suggestion | Closed | don't need
Issue_0059 | Reports (Ledger Report) |  | Status labels "Pending" and "Delivered" displayed in English when Japanese language selected. | 1. Set language to Japanese. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Reports → Ledger Report. 4. Observe status column. | Statuses shown in Japanese (e.g., "保留中" for Pending, "配信済み" for Delivered). | Statuses remain in English despite Japanese selection. | Issue_0059_LedgerReport_Lang.png | Low | Closed | N/A
Issue_0060 | Navigation (Menus)- iPad (7th generation) with iPadOS 18.5 - Safari | Functional | When the user clicks the "Settings" menu, the dropdown options — "Product Type," "Product," and "Hospitals" — do not respond when clicked. The same issue occurs with the "Reports" menu; its dropdown links, including "Loss Report" and "Ledger Report," are also unresponsive. | 1. Log in at https://suzu-service.com/linentech/. 2. Click Settings and try sub-options: "Product Type," "Product," "Hospitals". 3. Click Reports and try sub-options: "Loss Report," "Ledger Report". | Dropdown options respond and open their respective pages or sections. | Options do not respond; no action occurs on click. | Issue_0060_iPad_MenuUnresponsive.mp4 | Blocker | Closed |  | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0061 | Collections (Pre-Collection Form) | UI | Hospital input placeholder shows "No Define" when adding pre-collection. | 1. Log in at https://suzu-service.com/linentech/ 2. Navigate to Dashboard. 3. Select Pre-Collection. 4. Click Add +Pre-Collection. 5. Click Add New. 6. Observe the Hospital field placeholder. | Placeholder should display “Select Hospital” or appropriate text. | Placeholder incorrectly displays “No Define”. | Issue_0061_Hospital_Placeholder.png | Low | Closed
Issue_0062 | Collections (Pre-Collection Form) | UI | Page title shows "No Define" instead of "Pre-Collection". | 1. Log in at https://suzu-service.com/linentech/. 2. Navigate to Dashboard. 3. Select Pre-Collection. 4. Click Add +Pre-Collection. 5. Observe the page title. | Title should display "Pre-Collection". | Title incorrectly displays "No Define". | Issue_0062_NoDefine_Title.png | Low | Closed | N/A
Issue_0063 | Dashboard | UI | UI misalignment: "Clear" text overlaps start date field; "Search" button misaligned after clicking Search. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Dashboard. 3. Select start and end dates. 4. Click Search button. 5. Observe the header area. | "Clear" button, date fields, and "Search" button should be properly aligned without overlap. | "Clear" overlaps start date; "Search" button misaligned or not positioned correctly. | Issue_0063_Dashboard_Misalignment.png | Low | Closed |  | This issue has not been fixed
Issue_0064 | Dashboard - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Clear button too small and confusing after date search on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Dashboard. 4. Select start and end dates. 5. Click Search button. 6. Observe Clear button. | Clear button should be normal-sized and easy to understand/use. | Clear button appears too small and confusing for users. | Issue_0064_iPad_ClearButton.png | Low | Not a bug
Issue_0065 | Audit (Audit Page) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Audit Date column overlaps Hospital column on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to Audit page. 4. Observe table columns. | Columns should be properly aligned without overlap. | Audit Date overlaps Hospital column. | Issue_0065_iPad_AuditOverlap.png | Low | Closed |  | On iPad, the Lease Date field needs expansion; its icon overlaps the Lease No. icon Retest_Issue_0065_iPad_AuditColumnOverlap.png
Issue_0066 | AI (AI Page) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | AI page not responsive: chat box cut off, left thread list partially hidden on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari . 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to AI page. 4. Click Go To AI. 5. Observe page layout. | Responsive layout with full chat box and visible thread list on left. | Chat box cut off; thread list partially hidden. | Issue_0066_iPad_AIResponsive.png | Low | Closed
Issue_0067 | User Management | Functional | Adding new users and updating existing users fail; no response on submission. | Add New: 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to User. 3. Click Add New. 4. Fill required fields. 5. Click Add New to submit. Update: 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to User list. 3. Select a user and click Edit (pen icon). 4. Modify email field. 5. Click Update. | New user should be created/added to the list; updates should be saved and reflected. | No response; user not created/changes not saved. | Issue_0067_UserManagement_Bug.mp4 | Blocker | Closed |  | Payload: aePhoto: aeEmpId: 0 aePassword: aeFirstNameValue: Pandora Test aeEmail: tusetom@mailinator.com aeAccessKey: Pa$$w0rd! aeAccessKeyConfirm: Pa$$w0rd! aePhone: +1 (668) 212-9594 aeAddress: Esse nemo dolorum u aeDepartment: Exercitation aperiam aeDesignation: Non exercitation vel aeUserTypeId: 3 aeIsActive: A aeAccessKeyValue: Pa$$w0rd! Response: { "ErrorCode": "%PasswordPolicyMismatch%", "ErrorDescription": "Pass word should be minimum 6 characters with number, letter and symbol", "DataCount": null, "SubstituteID": null, "POAutoIDToReturn": null, "POStatusID": null, "SetID": null, "IsPromptShow": null }
Issue_0068 | In Android,Iphone 14 pro max |  | The leasing product shows a “Remove” button even though a “Delete” button already exists. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2.Navigate to Create New Lease page 3.Observe the page UI | Only one option (either “Remove” or “Delete”) should be displayed for the leasing product | The leasing product shows a “Remove” button even though a “Delete” button already exists. | https://drive.google.com/file/d/1xy6RojAF6-AQUTc4G_0S7AUb_8NCyNhO/view?usp=drive_link | Low | Closed | This not button it's label
Issue_0069 | User Management (Password Validation) | Functional | Password validation message unclear for special characters. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to User > Add New or Update User. 3. Enter a password with special characters (e.g., Pass$123!). 4. Submit the form. | Clear message: "Special characters are not allowed in passwords." | Generic validation message shown. | Issue_0069_Password_Validation.png | Medium | Not a bug
Issue_0070 | Create New Lease |  | Duplicate section appears on the “Create New Lease” page. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Add New Lease section and observe the result | Each section should appear only once on the “Create New Lease” page. | Duplicate section appears on the “Create New Lease” page. | https://drive.google.com/file/d/1NmXUMMsjgY0UWiiAITBJ2OY7AQaWa0Dv/view?usp=drive_link | Low | Closed
Issue_0071 | AI Page |  | After searching with input and filter, clicking the Clear button doesn’t show the default results. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to AI page 3.Set a date range 4.Select a hospital 5.Select one by one product and see the result 6.Now click on clear button and observe the result | After clicking the Clear button, the default results should appear as they did when first opening the page. | After searching with input and filter, clicking the Clear button doesn’t show the default results. | https://drive.google.com/file/d/1WrwS7ladzguym_T4SUIQlPbONEwYd9QK/view?usp=drive_link | Medium | Closed
Issue_0072 | Collection Page |  | When 15 kg is required, the system displays only 8 kg collected. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Collection 3.Require for 15 kg food items 4.Observe the board | The system should allow flexible combinations of available items to meet the required 15 kg — for example, collecting 2 pcs of chicken and 1 pc of vegetables (≈13 kg) or 1 pc of chicken and 3 pcs of vegetables (≈14 kg). | When 15 kg is required, the system displays only 8 kg collected. | https://drive.google.com/file/d/1uryB_G2evgjVKIQ5DRw4jAfyLu2lgfWv/view?usp=drive_link | High | Not a bug | This logic is as per requirment of client.So,there is not as we think.
Issue_0073 | AI (AI Page) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Chat thread list/history overlaps navigation bar on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to AI feature. 4. Chat in AI. 5. Observe the chat thread list. | No overlap; clear separation between chat history and navigation bar. | Chat history overlaps navigation bar text. | Issue_0073_iPad_AIOverlap.PNG | Low | Closed |  | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0074 | AI page | Functional | AI fails to generate a pie chart based on the provided table data | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to AI page 3.Click on the GoToAI 4.Now give command for pie chart generation | AI should successfully create and display a pie chart using the given table data | AI fails to generate a pie chart based on the provided table data | https://drive.google.com/file/d/1IoYV38IPIjXz2_edwVhid_csqgawi1Z4/view?usp=drive_link | Low | Not a bug | as per AI return
Issue_0075 | Leader Report |  | The UI layout for the Leader Report column is not displayed properly (misaligned ) | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Reports page 3.Choice Leader Report 4.Observe the column alignment | The Leader Report column should be properly aligned | The UI layout for the Leader Report column is not displayed properly (misaligned ) | https://drive.google.com/file/d/1ITMhRBDFAa9cZTQDLbNsxcex4bs6zYZM/view?usp=drive_link | Low | Closed
Issue_0076 | AI Page |  | After give any command AI page takes too much time to reponse | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to AI page 3.Filter by date and hospital 4.Click on Go to AI 5.Write something for get AI response | The AI page should respond quickly after a command is given. | After give any command AI page takes too much time to reponse | https://drive.google.com/file/d/1teZJaVJv7uejtwGB2a1pXC4hf8HA3lf1/view?usp=drive_link | Medium | Not a bug
Issue_0077 | Inventory Page | Functional | When a user adds any product to a hospital from the inventory room section, the data fails to save and shows all values as 0. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Reports page 3.Choice Leader Report 4.Observe the column alignment | The product details and quantity should be saved correctly and displayed with accurate values after adding. | When a user adds any product to a hospital from the inventory room section, the data fails to save and shows all values as 0. | https://drive.google.com/file/d/1PpwuGeWPf0A06ebt3kxDX_-L_mRx4FuM/view?usp=drive_link | High | Closed
Issue_0078 | Leasings (Create New Lease Form) | UI | “Initial Lease” button not visible without scrolling; only appears after scrolling. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Dashboard > Leasings > Add Lease. 3. Observe page on load. 4. Scroll down. | Button should be visible on initial load or fixed for easy access. | Button hidden at bottom; requires scrolling to view. | Suggestion_0078_InitialLease_Visibility.mp4 | Suggestion | Closed |  | This is not an issue; it’s just a suggestion for improvement.
Issue_0079 | AI Page | Functional | When trying to delete any chat, a blank popup appears with No define message. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to AI page 3.Click on the Go to AI 4.Try to delete a chat and observe the pop up message | A confirmation message should appear in the popup when deleting a chat | When trying to delete any chat, a blank popup appears with No define message. | https://drive.google.com/file/d/1xdpCF_OkTkHcyQIJrbYGEzttDfAobt20/view?usp=drive_link | Low | Closed
Issue_0080 | Collections (New Collection Form) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Staff select field cut off; full input not visible on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Dashboard > Collections > New Collection. 4. Observe Staff select field. | Full select field visible without cutoff. | Field cut off; not fully visible. | Issue_0080_iPad_StaffField.mp4 | Low | Closed |  | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0081 | Settings | Functional | Room limit is not working properly — even after setting a limit of 2 rooms, users can still add more rooms after refreshing the page, and those extra rooms show up later in the lease form. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Settings → Hospitals → Add New. 3. Create a new hospital and set Room Limit = 2. 4. Try to add 3 or more rooms — you’ll see an error message like “Reached room limit.” 5. Refresh the page. 6. Go to Dashboard → Leasings → Add Lease. 7. Select the hospital you just added and check the Room list. | The system should allow adding only 2 rooms, and after refreshing, only those 2 should remain visible in both the Hospital and Lease pages. | After refreshing, all previously added rooms (even beyond 2) appear again. The lease form shows 3 or more rooms with incorrect data (e.g., negative remaining values). | Issue_0081_RoomLimit_NotWorking.mp4 | High | Closed | N/A
Issue_0082 | User Management (Add New User Form) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Password visibility (eye) icon overlaps the placeholder text inside password fields. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Go to User → Add New. 4. Check the Login Password and Confirm Password fields. | Eye icon should be properly aligned and not overlap the placeholder text. | Eye icon overlaps the placeholder text (e.g., “Password should be minimum…”). | Issue_0082_iPad_PasswordIcon.png | Low | Closed
Issue_0083 | User Management (View Users Page) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Table columns overlap; Phone overlaps Address, Address overlaps Designation, and Name/Email columns have excessive spacing. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to User → View Users. 4. Observe the user list table. | All columns properly aligned with even spacing; no overlaps between fields. | Phone column overlaps Address; Address overlaps Designation; Name and Email columns have unnecessary extra space. | Issue_0083_iPad_UserTableOverlap.mp4 | Low | ReOpen | If this solution is ok for Ipda,please let me know | Suggestion_0083_iPad_UserTableLayout.mp4 watch this video — it has my UI improvement suggestions
Issue_0084 | Inventory Report Page | Functional | The Export button is not functioning, no file is generated or downloaded. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Inventory Report section 4. Click on export button and observe the result | System should generate the export file and automatically download | The Export button is not functioning, no file is generated or downloaded. | https://drive.google.com/file/d/1pV68NLB9bHkE2QtPLVxc1BS6CGiGLqJF/view?usp=drive_link | High | Closed
Issue_0085 | Leasing | Functional | When leasing a product with quantity 0 and clicking Initiate, it initiated, but the product does not appear in the pending leasing list. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Leasing 4. Click on Add new 5.Lease any product with 0 input and click on initiate lease | The system should not allow leasing 0 quantity and should show an error message. | When leasing a product with quantity 0 and clicking Initiate, it initiated, but the product does not appear in the pending leasing list. | https://drive.google.com/file/d/1r3z35hEFhUMLNgl6Pk5pgjeR9Gg0Y0B8/view?usp=drive_link | Medium | Closed
Issue_0086 | Dashboard- Search | Functional | When searching by date filter in the Dashboard (Leasing section), the system automatically shows Pre-collection results and navigates to the Pre-collection section. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Leasing 4.Select starting and ending date from the serach filter 5.Click on search button and observe the result | The date filter in the Leasing section should show results only for Leasing and should not navigate to the Pre-collection section. | When searching by date filter in the Dashboard (Leasing section), the system automatically shows Pre-collection results and navigates to the Pre-collection section. | https://drive.google.com/file/d/1Rsl3rVDR82ZuI40r5HmgowVIln36NpmG/view?usp=drive_link | Medium | Closed
Issue_0087 | Dashboard- Search | Functional | The Hospital ,Product Type filter is not working in the Pre-collection section. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Leasing 4.Select starting and ending date from the serach filter 5.Click on search button 6.Select any hospital and observe the result | All filter should correctly display only the records related to the selected hospital in the Pre-collection section. | The Hospital ,Product Type,Driver filter is not working in the Pre-collection section. | https://drive.google.com/file/d/1-EBz15dykdyXwI6HKaPADqVNpYwJo-At/view?usp=drive_link | High | Closed
Issue_0088 | LoginPage | Functional | When trying to log in with a valid email and an invalid password, the system does not show any error message. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to Leasing 4.Select starting and ending date from the serach filter 5.Click on search button 6.Select any hospital and observe the result | The system should display an error message such as “Invalid password” when the password is incorrect. | When trying to log in with a valid email and an invalid password, the system does not show any error message. | https://drive.google.com/file/d/1hE03_zQ-u1FqR_Sl_00fPeLeKwVqyx7b/view?usp=drive_link | High | Closed
Issue_0089 | LoginPage(web and android) | UI | The product capacity column is not aligned properly. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to settings-Hospitals 3.Click on any hospital 4.Again select any room details and observe the result | The product capacity column data should be aligned with the other columns. | The product capacity column is not aligned properly. | https://drive.google.com/file/d/1Rki7cLeUX3WIxyBZ013u_waRU3RFZH7h/view?usp=drive_link | Low | New
Issue_0090 | Product,Hospitals,Inventory room(android) | UI | In Android, the Product, Inventory Room, and Hospitals page show two separate scrolls (one for the title and one for the listed data), which confuses users when entering data. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Go to settings-Hospitals,Inventory room,Product 3.Observe each page scroll | There should be a single smooth scroll so users can view the title and listed data together without confusion. | In Android, the Product, Inventory Room, and Hospitals page show two separate scrolls (one for the title and one for the listed data), which confuses users when entering data. | https://drive.google.com/file/d/1IViBefDB7ZU99ebYzw6RSrtvJnnAI4r7/view?usp=sharing | Low | Closed
Issue_0091 | Settings (Product Type Page)-iPad (7th generation) with iPadOS 18.5 and Chrome | UI | "Add New" button displayed in excessively large size. | 1. Use iPad (7th generation) with iPadOS 18.5 and Chrome. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Settings > Product Type. 4. Observe "Add New" button. | Button displayed in normal size, fitting layout. | Button stretched and too big. | ssue_0091_iPad_AddNewButtonLarge.mp4 | Low | Closed |  | Please watch the attached video. It shows the issue and my suggestions.
Issue_0092 | Settings (Product Page) -iPad (7th generation) with iPadOS 18.5 and Chrom |  | Product table columns overlap; one column overlays next columns. | 1. Use iPad (7th generation) with iPadOS 18.5 and Chrome. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Settings > Product. 4. Observe the product table. | Columns properly aligned without overlaps. | One column overlaps next (e.g., status overlaps actions/description). | Issue_0092_iPad_ProductTableOverlap.png | Low | New
Issue_0093 | Settings (Hospitals Page)-iPad (7th generation) with iPadOS 18.5 and Chrom | UI | Hospital table columns overlap; background shadow cut off/not fully displayed. | 1. Use iPad with Chrome browser. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Settings → Hospitals. 4. Observe the hospital table. | Columns properly aligned without overlap; full background shadow displayed. | Columns overlap (e.g., Hospital Name over Inventory Room); shadow cut off. | Issue_0093_HospitalsPage_UI_1.png Issue_0093_HospitalsPage_UI_2.png | Low | Closed
Issue_0094 | Reports (Sidebar Menu) | UI | Loss Report and Ledger Report use the same icon/logo. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Reports. 3. Observe sub-menu items. | Distinct icons for Loss Report and Ledger Report. | Same icon displayed for both. | Issue_0094_ReportsMenu_IconDuplicate.png | Low | Closed
Issue_0095 | Pre collection page | Functional | In the Pre-Collection section, when products are added from two different hospitals, after confirming, the system shows only one hospital name. This creates a problem when searching by hospital. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Login as admin 3.Go to pre collection and add product from 2 different hospitals 4.Confirm the pre collection and observe the result | After confirming, the system should either: Show both hospital names separately, so users can search by each hospital correctly, OR Allow only one hospital for Pre-Collection at a time to avoid mixing data. | In the Pre-Collection section, when products are added from two different hospitals, after confirming, the system shows only one hospital name. This creates a problem when searching by hospital. | https://drive.google.com/file/d/1Jv2aaZ0Nv_W8ZNbLrm5BiJuW1iE9js33/view?usp=drive_link | Medium | Closed
Issue_0096 | Add Leasing Page | Functional | After adding the second product from the 2nd room and initializing the lease, the Driver Name field does not show an error message when left empty. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Login as admin 3.Go to lease and add one product from one room 4.Now click on submit 5.Again select another room and add one product from different room 6.Confirm the leaseing and observe the result | The system should show a proper error message if the Driver Name field is empty during lease initialization. | After adding the second product from the 2nd room and initializing the lease, the Driver Name field does not show an error message when left empty. | https://drive.google.com/file/d/1-grqZp-6GNINcfgkMP6em6SyXCkFA6E9/view?usp=sharing | Low | Closed
Issue_0097 | Android | UI | Only login UI should display in android | 1.Navigate to the Url: https://suzu-service.com/linentech/. 2. Observe the login form in android | Only login UI should display in android | A picture displayed with login UI | https://drive.google.com/file/d/1y7cr2lH7j2XfJC8TDuzUESaTLP8h3IYe/view?usp=drive_link | Low | Closed
Issue_0098 | Settings (Hospitals Page)- iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Hospital table columns overlap each other. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/ 3. Navigate to Settings > Hospitals. 4. Observe the table columns. | Columns properly aligned without overlap. | Columns overlap (e.g., Hospital Name over Inventory Room). | Issue_0098_iPad_HospitalTableOverlap.PNG | Low | Closed
Issue_0099 | User Management (View Users Page) | UI | Column values for Email, User Type, Status not aligned with headers. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to User > View Users. 4. Observe table columns. | Values aligned under respective headers (Name, Email, User Type, Status). | Values misaligned (e.g., Email under User Type, shifted layout). | Issue_0099_UserTableMisaligned.png | Low | ReOpen
Issue_0100 | Settings (Product Type Page) | UI | Product Type table displayed too small, affecting readability. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to Settings > Product Type. 4. Observe the table. | Table sized normally for full visibility and readability. | Table rendered small, compressed layout. | Issue_0100_ProductTypeTableSmall.png | Low | New
Issue_0101 | Settings (Product Page) | UI | Header titles like Type, Unit (Kg) not aligned with data columns. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to Settings > Product. 4. Observe table headers and data. | Headers aligned with corresponding data columns. | Headers misaligned (e.g., Type over Unit, data shifted). | Issue_0101_ProductTable_UI.png | Low | ReOpen
Issue_0102 | AI (AI Page) - iPad (7th generation) with iPadOS 18.5 and Safari. | UI | Chat thread list/history overlaps navigation bar on iPad. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to AI feature. 4. Chat in AI. 5. Observe the chat thread list. | No overlap; clear separation between chat history and navigation bar. | Chat history overlaps navigation bar text. | Issue_0073_iPad_AIOverlap.PNG | Low | New |  | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0103 | Settings (Inventory Room Page) | UI | Inventory Room table header "Room Name" not aligned with data column. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to Settings > Inventory Room. 4. Observe table headers and data. | Headers aligned with data columns (Hospital Name, Room Name, Product Count, Capacity). | "Room Name" header misaligned with its data column. | Issue_0103_InventoryRoom_UI.png | Low | New |  | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0104 | Audit (Audit Page) | UI | Audit table headers "Audit Date" and "Audit By" not aligned with data columns. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to Audit page. 4. Observe table headers and data. | Headers aligned with data (AuditNo, AuditDate, AuditBy, Status). | "Audit Date" and "Audit By" headers misaligned with data. | Issue_0104_Audit_HeaderMisaligned.png | Low | New |  | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0105 | Collection(In android) | Functional | In the Android, Collection section, the user cannot enter any value in the Weight field. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Collection section 3. Click on Add collection 4.Try to input weight and observe the result | The user should be able to type and save the Weight value without any issue. | In the Android, Collection section, the user cannot enter any value in the Weight field. | https://drive.google.com/file/d/1K5mDG192QPG5CwGfzR4WBO3Tu_IHzNH6/view?usp=sharing | High | New
Issue_0106 | Dashboard | Functional | When leasing some items from the same hospital, after applying product type filter on the dashboard, the displayed information is incorrect. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Add leasing 2 items from a hospital and delivered 3.Now search them using date,hospitals and product type filter 4.Now compare the leasing quantity and dashboard data | should display correct leasing quantity | When leasing some items from the same hospital, after applying product type filter on the dashboard, the displayed information is incorrect. | https://drive.google.com/file/d/1SdP6Q72KV4ceHzTNOU7-BKlDAh-gf_mk/view?usp=sharing | High | Closed
Issue_0107 | Loss Report | Functional | When leasing some items from the same hospital, after applying product type filter on the loss report, the displayed information is incorrect. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Add leasing 2 items from a hospital and delivered 3.Now search them using date,hospitals and product type filter 4.Now compare the leasing quantity,loss amount with loss report data | should display correct leasing,loss amount | When leasing some items from the same hospital, after applying product type filter on the loss report, the displayed information is incorrect. | https://drive.google.com/file/d/1SdP6Q72KV4ceHzTNOU7-BKlDAh-gf_mk/view?usp=sharing | High | Closed
Issue_0108 | Reports (Loss Report) - iPad (7th generation) with iPadOS 18.5 and Safari | UI | Table headers (Hospital, Product, In-Stock, Loss Rate) are not aligned with their respective columns. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Log in as Admin at https://suzu-service.com/linentech/. 3. Navigate to Reports > Loss Report. 4. Observe the table headers. | Headers should be properly aligned with the corresponding data columns. | Headers are misaligned (e.g., Hospital and Product columns shifted). | Issue_0108_iPad_LossReportHeader.png | Low | New | iPad (7th generation, iPadOS 18.5, Safari)
Issue_0109
Issue_0110
Issue_0111
Issue_0112
Issue_0113
Issue_0114

## LinenTech Language Bug Report
Created By | QA Harbor Limited | Title | Issue report for LinenTech | Website URL | https://suzu-service.com/linentech/ | Environment | Windows 10,Google Chrome 131.0.6778.86 MacOS Linux Browser: Chrome,Mozilla firefox,Microsoft Edge
Bug ID | Module | Issue Summary | Steps to reproduce | Expected result | Actual result | Attachments | Priority | Bug Status | Dev Comment | Tester Comment | Date
Language_Issue_001 | Web-Leasing | Title are overlapped with another section | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Leasing 3.Click on Add new and observe the UI | Should not overlap with another section | In Japanese,title are overlapped with another section | https://drive.google.com/file/d/1UYjfFmpC2-sH6OgRUTEFX61POpGlR7pb/view?usp=drive_link | Low | New
Language_Issue_002 | Web-Pre Collection | In the Pre-collection section, the button names are not in Japanese. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Pre collection 3.Click on Add new and observe the marked button name | should be displayed in Japanese as per the language settings | In the Pre-collection section, the button names are not in Japanese. | https://drive.google.com/file/d/1CHUU-fM7xVql2Ega3A1E3PX_WziP9qWT/view?usp=drive_link | High | Closed
Language_Issue_003 | Web-Pre Collection | In the Pre-collection section, alert messages are not in Japanese. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Pre collection 3.Click on Add new and without insert any data 4.Click on confirm | All alert messages in the Pre-collection section should be displayed in Japanese according to the language settings. | In the Pre-collection section, alert messages are not in Japanese. | https://drive.google.com/file/d/1OR6cmWHcvOLOI0pvj0CYqactUP4PlpCY/view?usp=drive_link | High | Closed
Language_Issue_004 | Web-Audit | In the Audit section, alert messages are not displayed in Japanese. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Audit 3.Click on Add new and without insert any data 4.Click on confirm | All alert messages in the Audit section should be displayed in Japanese according to the language settings. | In the Audit section, alert messages are not displayed in Japanese. | https://drive.google.com/file/d/11c6RuH1tNm2FZEIwLE6KngPIzQDnn0mh/view?usp=drive_link | High | Closed
Language_Issue_005 | Web-Audit | Error message not in Japanese when keeping audit stock as 0 | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to Audit 3.Click on Add new 4.Select hospital and see the product stock 5.Now make audit stock 0 and click on update | When the audit stock is set to 0, the error message should be displayed in Japanese according to the language settings. | Error message not in Japanese when keeping audit stock as 0 | https://drive.google.com/file/d/1IO5m_hcFh6X-f2-I29xJOHp2ayon7Uvn/view?usp=drive_link | High | Closed
Language_Issue_006 | Web-AI | Alert message not in Japanese when deleting chat history | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Navigate to AI Page 3.Click on GOtoAI 4.Delete any chat history and observe the result | The confirmation popup message should be displayed in Japanese according to the language settings. | Alert message not in Japanese when deleting chat history | https://drive.google.com/file/d/1deJtiK9YAT9XGOmb720U8A4A0_iyvyLv/view?usp=drive_link | High | Closed
Language_Issue_007 | Web-Login Page | When trying to log in with all fields blank, the error messages are not in Japanese. | 1.Navigate to the url: https://suzu-service.com/linentech/. 2.Keep all field blank 3.Click on login | All error messages for blank login fields should be displayed in Japanese according to the language settings. | When trying to log in with all fields blank, the error messages are not in Japanese. | https://drive.google.com/file/d/1YgRtlPE1d_d8XHtT9xP0lN29hUtyeJm0/view?usp=drive_link | High | Closed
Language_Issue_008 | Web-Collection | The date format/text on the Collection page is not in Japanese. | 1.Navigate to the url: https://suzu-service.com/linentech/. 2.Login as Admin 3.Go to collection section and observe the marked text | The date on the Collection page should be displayed in Japanese according to the language settings. | The date format/text on the Collection page is not in Japanese. | https://drive.google.com/file/d/1V1VhyUBE03S25Siyf-26fMzr7m7lWy1W/view?usp=drive_link | High | Closed
Language_Issue_009 | Leasings (Create New Lease Form) - iPad (7th generation) with iPadOS 18.5 and Safari. | Inventory rooms show invalid/garbled text when Japanese language is selected. | 1. Log in as Admin at https://suzu-service.com/linentech/. 2. Select Japanese language. 3. Navigate to Leasings > +Add Lease. 4. Select Driver and Hospital Name. 5. Observe the inventory rooms list. | Rooms should display correct Japanese text with proper encoding. | Rooms appear as garbled/encoded strings (e.g., “リンネ室R1”). | Language_Issue_009_iPad_JapaneseTextError.mp4 | Low | New | N/A
Language_Issue_010 | Collections (New Collection Form) | In Japanese language, PreCollectionDate shows "%lblDate%" instead of proper label. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Select Japanese language. 3. Log in at https://suzu-service.com/linentech/. 4. Navigate to Add Collection. 5. Observe the PreCollectionDate field. | Proper Japanese label should appear (correct translated date field). | Placeholder shows invalid text "%lblDate%". | Language_Issue_010_Japanese_LabelMissing.png | Low | Ready for testing |  | iPad (7th generation, iPadOS 18.5, Safari)
Language_Issue_011 | Collections (Add Pre-Collection Form) - iPad (7th generation) with iPadOS 18.5 and Safari. | Page title and Confirm button show placeholders "%PreCollectionTitle%" and "%btnConfirm%" in Japanese language. | 1. Use iPad (7th generation) with iPadOS 18.5 and Safari. 2. Select Japanese language. 3. Log in at https://suzu-service.com/linentech/. 4. Navigate to Add Pre-Collection. 5. Observe page title and Confirm button. | Proper Japanese text for title ("事前回収追加") and button ("確認"). | Placeholders "%PreCollectionTitle%" and "%btnConfirm%" displayed. | Language_Issue_011_PreCollection_Title_BTN_Bug.png | Low | Ready for testing | iPad (7th generation, iPadOS 18.5, Safari)
Language_Issue_012 | Pre collection | In pre collection section when add 0 bag and try to save it display an erro which means 納品数(delivery quantity) | 1. Select Japanese language. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Add Pre-Collection. 4. Add 0 in the bag and try to submit | should display proper error message in japanese | In pre collection section when add 0 bag and try to save it display an erro which means 納品数(delivery quantity) | https://drive.google.com/file/d/1MVl9BeqOEMZ5nCVvzhgdmnO2ekS0K3Fl/view?usp=drive_link | Medium | New
Language_Issue_013 | Leasing | In the leasing section, when no inventory room is added and I try to add a new one, the message shows “No room available” in English instead of Japanese. | 1. Select Japanese language. 2. Log in at https://suzu-service.com/linentech/. 3. Navigate to Add Leasing 4. Add a hospital which has no inventory room | The message should be displayed in Japanese according to the system language. | In the leasing section, when no inventory room is added and I try to add a new one, the message shows “No room available” in English instead of Japanese. | https://drive.google.com/file/d/1WGL6q5fUK0PLtVT2PJ2soR9DG0l9d0c9/view?usp=drive_link | Low | New

## Loss Calculation
Prev Stock | Lease | Collection | Stock | Difference | Lease Loss | Loss | When lease loss 0 Loss=(Total collection - total lease) | Loss Rate= (loss/lease)*100
0 | 10 | 0 | 10 | 0 | 0 | 0 | -10
10 | 2 | 0 | 13 | 1 | -1 | -1 | -2
13 | 2 | 0 | 14 | -1 | 1 | -14 | -2
14 | 0 | 5 | 9 | 0 | -9 | -9 | 5
9 | 0 | 10 | 0 | 0 | 1 | 1 | 10
[5 empty] | 0 |  | 0
Prev Stock |  | Collection | Stock |  | Lease Loss | Lease | When lease loss 0 Loss=(Total collection - total lease) | Loss Rate= (loss/lease)*100
0 |  | 0 | 10 |  | -10 |  | 0
10 |  | 0 | 13 |  | -3 |  | 0
13 |  | 0 | 14 |  | -1 |  | 0
14 |  | 10 | 4 |  | 20 |  | 10
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0

## demo Calculation record
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
12 | 20 | 60 | 20 | 0 | 0% | The system should allow flexible combinations of available items to meet the required 15 kg — for example, collecting 2 pcs of chicken and 1 pc of vegetables (≈13 kg) or 1 pc of chicken and 3 pcs of vegetables (≈14 kg).
35 entry for vegetable
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
12 | 50 | 95 | 20 | -5 | -10%
Collected 20 pcs Multiple product 1
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
12 | 50 | 75 | 40 | -5 | -10%
Collected 16pc vegetables
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
12 | 50 | 59 | 56 | -5 | -10%
After add 20 memory foam pillow
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
12 | 70 | 79 | 56 | -5 | -7%
30 pc collected memory foam pillow
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
12 | 70 | 59 | 86 | -5 | -7%
Lease 20 but give input 30
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
15 | 20 | 30 | 0 | -10 | -50%
lease 5 but give 10
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
15 | 25 | 40 | 0 | -15 | -60%
collected 1 pc vege
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate
15 | 25 | 39 | 1 | -15 | -60%
After stock 30 pcs from Audit
Hospital | Leased | Hospital In-Stock | Collected | Loss | Loss Rate | Previous Stock | Audit Stock | Loss | Loss Rate
15 | 25 | 69 | 1 | -15 | -60% | 0 | 30 | 30 | 0%